Table of Contents

# TechScreen — MVP Scope Document

Version: 0.2 (draft for review) Owner: Ihor Date: 2026-04-18 Status: Draft

## 1. Context & Problem

Current state. Technical interviews for engineers are conducted by live tech experts. Each interview takes 1–1.5 hours of an expert’s time plus prep and post-interview feedback. This creates a bottleneck on the expert role and slows hiring throughput.

Secondary problem. Interview quality depends on the individual expert — inconsistent calibration, different questioning styles, and varying assessment depth. There is no single reference scoring source.

Secondary need. Internal engineers would benefit from a practice tool — mock interview sessions with feedback — for interview preparation.

Goal of TechScreen. An automated AI system that runs standardized technical interviews, produces structured feedback, and gradually replaces or augments live tech experts. A secondary role is serving as an internal training tool.

## 2. MVP Goals

- Run 10+ real pilot interviews end-to-end without critical bugs.

- Achieve ≥70% inter-rater agreement between the AI Assessor and a human reviewer on competency-level scores.

- Collect ≥50 annotated turns as a seed dataset for future RAG and potential fine-tuning.

- Validate the technical architecture (agents + Vertex + state machine + annotation pipeline) on real data — unblock Phase 2.

## 3. Out of Scope (MVP)

Explicitly not in the MVP:

- Voice interface. Text-only. Architecture is voice-ready (WebSockets, async assessment, streaming, transport-agnostic core).

- JD Parser. Recruiter fills Position Template manually.

- RAG over past annotations (feature-on). Infrastructure (embeddings, vector index) is present; feature flag OFF until 20–30 annotated interviews are collected.

- Model fine-tuning. Prompt + context engineering only.

- Advanced anti-cheating (proctoring, screen recording, behavioral detection). Basic deterrent only (candidate warning).

- Meet / Teams integration. Candidate-facing UI runs in the company’s web browser.

- Third stack beyond C# and React. MVP covers only these two competency trees.

- Candidate self-service account. Candidate gets a link and runs the session; no personal account.

- Bias / fairness audit. Requires more data; Phase 2+.

- Admin UI for rubric editing. MVP edits rubric via YAML in Git (Configs-as-Code).

## 4. Personas & User Stories

Persona 1 — Recruiter - Creates Position Templates for open roles - Triggers InterviewPlan generation, reviews and edits it, approves - Sends invite links to candidates - Reviews final reports

Persona 2 — Reviewer (tech expert) - Reviews completed sessions (transcript + TurnTrace) - Annotates turn quality (TurnAnnotation) - Overrides Assessor scores via AssessmentCorrection - Signs off final decision

Persona 3 — Candidate - Receives invite link, runs a text-based session (60–90 min) - Provides consent for recording (GDPR baseline) - Candidate-facing feedback is deferred to Phase 2

User Stories: - US-1. Recruiter creates an interview for a Middle C# + React role and obtains an approved plan in ≤15 min. - US-2. Candidate runs the session; the system scores each turn in near real time; the Assessor produces per-competency scores. - US-3. Reviewer opens a completed session, sees the full transcript with per-turn assessments, and annotates / corrects it in ≤30 min. - US-4. System exports an annotated dataset for accumulation and future training.

## 5. High-Level Architecture (summary)

Full details in the Architecture Document.

Key components: - Frontend (Next.js) — Recruiter Admin, Candidate Session, Reviewer Annotation - Backend API (Python / FastAPI) — REST + WebSockets - Orchestrator (deterministic state machine) — drives phase transitions, invokes agents, persists TurnTrace - Agents (Vertex AI) — Interviewer, Assessor, PreInterviewPlanner - Database (PostgreSQL / Cloud SQL) — sessions, plans, turns, annotations, rubric - Vector Index (pgvector) — RAG infrastructure, feature-off in MVP - Observability — TurnTrace log, cost tracking, latency metrics

External dependencies: Google Workspace SSO (Identity Platform), Vertex AI Model Garden (Gemini + Claude Sonnet via Model Garden).

## 6. Detailed Phase Breakdown (12 weeks, 2 engineers)

Team roles: - Engineer A — Backend / ML. FastAPI, Vertex integration, agents, prompts, state machine, DB, evals, calibration. - Engineer B — Full-stack frontend + glue. Next.js UI, admin screens, annotation UI, infra / CI / deploy, observability dashboards.

Each week below lists: Goal → Deliverables (by layer) → Acceptance Criteria.

### W1–W2: Foundation & Setup

Goal. Team can write, test, and deploy code. Vertex is reachable. No product features yet — pure infrastructure.

Deliverables: - Repo / tooling — monorepo layout (backend/, frontend/, prompts/, adr/, docs/, evals/, infra/), pre-commit hooks, lint / type-check, pytest, Jest, CI pipeline (lint + test on PR). - Backend skeleton — FastAPI project with health endpoint, settings via Pydantic, structured logging, dependency injection layout. - Frontend skeleton — Next.js (App Router, TypeScript, Tailwind, shadcn/ui), admin shell layout with navigation. - Infra — Cloud Run services (backend + frontend), Cloud SQL instance (dev + staging), Google Secret Manager, environment configs, baseline Cloud Logging + Error Reporting. - Auth — Google Workspace SSO integration (Identity Platform or NextAuth with Google provider), role claims (admin / recruiter / reviewer). - DB schema v0 — users, sessions placeholder, rubric tables (Stack, CompetencyBlock, Competency, Topic, Level). Alembic migrations set up. - Vertex client wrapper — generic call interface for Gemini + Claude via Model Garden, retries, timeouts, cost tracking middleware hook. - Matrix importer — Python script reading the competency matrix .xlsx, validating, emitting canonical YAML into configs/rubric/. Seed script loads YAML into DB on deploy.

Acceptance: - Local dev: both services run with one command. - PR opens → CI green. - Deploy to staging works (one-click). - Vertex call from backend returns a response (smoke test). - Running the matrix importer on the provided .xlsx produces valid YAML and loads the rubric into the DB.

### W3: Position Template + Rubric Snapshot

Goal. Recruiter can create / edit a Position Template; system can snapshot the rubric immutably for a session.

Deliverables: - Backend — Position Template CRUD endpoints, validation against rubric, rubric snapshot logic (deep-copy into InterviewSession.rubric_snapshot), Configs-as-Code pipeline (YAML in Git → validation → DB sync on merge). - Frontend — Position Template list view, create / edit form (pick stacks, level, must-have competencies, optional). - Data model — Position Template entity; rubric snapshot column on session.

Acceptance: - Recruiter creates a Position Template from the UI. - Session start pins an immutable rubric snapshot; post-start rubric edits do not affect the snapshot. - Editing a YAML config in Git flows to the DB on merge.

### W4–W5: Core Agents & State Machine

Goal. End-to-end mock conversation loop works: candidate types → Interviewer responds → Assessor scores each turn.

Deliverables: - Prompts Repository — prompts/interviewer.md, prompts/assessor.md, each with system prompt, output JSON schema, few-shot block. Versioning via semver tags. - Interviewer Agent — deterministic wrapper: builds prompt from template + session state, calls Vertex, validates output against schema, retries on schema failure. - Assessor Agent — same wrapper pattern; outputs per-turn concept coverage + red flags + confidence. - State machine (Orchestrator) — phases: INTRO → TECH (per competency → per topic → probes) → QA → CLOSE. Transitions are deterministic code, not LLM-driven. Supports skip / probe decisions based on agent suggestions. - TurnTrace logger — captures every agent invocation: full prompt, raw response, parsed output, token counts, latency, model, agent type, cost. - Cost tracking middleware — per-session running total, exposed via metrics. - Dev conversation UI — minimal, non-branded UI used by the team to drive sessions end-to-end for testing.

Acceptance: - A complete mock interview session runs start-to-finish without manual intervention. - Every turn has a TurnTrace row. - All agent outputs validate against their schemas (or are retried / logged on failure). - Changing a prompt version is a single-file change in prompts/, picked up on deploy.

### W6: PreInterviewPlanner + Recruiter Review UI

Goal. Recruiter can generate, review, edit, and approve an InterviewPlan before the session starts.

Deliverables: - PreInterviewPlanner Agent — generates a plan from Position Template + rubric snapshot: ordered competencies, target minutes, topics with target level and priority, seed questions. - InterviewPlan data model — plan_json blob, generated_by, approved_by, approved_at, status (draft / approved / frozen). - Freeze mechanism — on session start, plan becomes immutable; edits after start are blocked. - Recruiter Review UI (simplified) — list of competencies / topics in order with time estimates; inline edit of seed question text; add / remove topic; reorder; mark priority (must_cover / nice_to_have); Approve button transitions to approved.

Acceptance: - From a fresh Position Template, recruiter generates + edits + approves a plan in under 15 minutes. - Session start pins the plan; post-start edits are rejected. - Plan JSON is readable and diffable in observability tools.

### W7: Candidate Session (end-to-end UX)

Goal. A real candidate can enter via link, run a timed interview, and the session saves reliably.

Deliverables: - Backend — session start endpoint (magic link token or SSO), WebSocket channel for turn streaming, consent gate before first message, auto-save after every turn, timeout / expiration handling, graceful close. - Frontend — candidate landing page (intro + consent), chat-style session UI (clean, minimal, internal branding), connection-lost handling, progress indicator (phase + elapsed time). - Reliability — if the candidate loses connection, they can reconnect within the session window without losing state.

Acceptance: - Candidate receives a link → consents → runs a full 60–90 min session → session persists completely. - Closing the browser mid-session and reopening within 30 min resumes the session. - Hard timeout (e.g. 120 min) gracefully closes and saves a partial session.

### W8: Reviewer / Annotation UI

Goal. Reviewer can open a completed session, see transcript and scores, annotate, correct, and sign off.

Deliverables: - Backend — session detail endpoint (transcript + TurnTrace + Assessor outputs + final scores), TurnAnnotation CRUD, AssessmentCorrection CRUD, final decision endpoint (approve / reject / request-more-info), basic report generation (Markdown template rendered from session). - Frontend — Reviewer session detail page with turn-by-turn view, Assessor output panel side-by-side, annotation controls (quality tags + free text) per turn, correction controls (override score + reason tags) per competency, final decision controls. - Export — final report as Markdown (downloadable); printable view.

Acceptance: - Reviewer completes annotation of one 60-min session in ≤30 min. - All edits persist and are visible in DB and audit log. - Final report is exportable and shareable.

### W9: Observability & Evals

Goal. Team has dashboards to debug quality and cost; golden dataset framework is in place.

Deliverables: - Observability — cost / latency / error-rate dashboards (Cloud Monitoring or Grafana), per-agent metric charts, alert rules (cost per session > threshold, p95 latency > 20 s, error rate > 5%). - TurnTrace viewer — internal page to search / filter traces, view raw prompts and responses, diff prompt versions. - Golden dataset framework — evals/ folder with JSONL golden sets per agent; script runs agent against golden set and reports metrics (coverage agreement, schema validity). - Synthetic alert test — trigger each alert at least once to confirm wiring.

Acceptance: - Team can open dashboards and see rolling trends. - Running eval CLI against a golden set produces a baseline report per agent. - All alerts fire on synthetic overrun tests.

### W10: Calibration

Goal. Prompts are tuned on known candidates; model A/B decision made; system is ready for real pilot.

Activities: - 3–5 internal calibration interviews (internal engineers role-playing known strong / weak / middle candidates). - Prompt iteration based on TurnTrace review (lock once stable). - A/B test Gemini 2.5 Pro vs Claude Sonnet 4.6 on identical interview prompts; decision documented in an ADR. - Reviewer dry-runs to validate annotation UX on real sessions. - Identify and fix critical bugs; freeze prompt versions for pilot.

Acceptance: - Known strong / weak / middle candidates receive the expected assessment (within a documented tolerance). - Model choice for pilot documented in ADR. - No P0 / P1 bugs open. - Prompt versions tagged for pilot (e.g. interviewer-v1.0-pilot).

### W11: Pilot Preparation

Goal. Everything needed to launch with real candidates is in place.

Activities / Deliverables: - Security review (SSO, secret handling, data access audit, dependency scan). - Candidate consent flow finalized (legal review if required). - Pilot operations playbook (how recruiters assign interviews, incident handling, escalation path). - Candidate-facing comms templates (invitation email, intro page copy, FAQ). - Final QA pass across all flows. - Data retention policy + GDPR baseline implemented (delete endpoint, retention window). - Full dry-run with 1 internal candidate through the real pilot flow.

Acceptance: - Security sign-off received. - Ops playbook approved. - No P0 / P1 bugs open. - Dry-run completed successfully.

### W12: Pilot Execution

Goal. Run real pilot, collect metrics, validate success criteria.

Activities: - 10+ real candidate interviews, each followed by reviewer annotation + correction. - Metrics collection against section 7 criteria. - Daily triage of incidents and quick fixes (no new features). - Retrospective with engineers + recruiters + reviewers. - Decision gate: proceed to Phase 2, iterate MVP, or pivot.

Acceptance: - ≥10 completed interviews. - Metrics from section 7 measured and documented. - Retrospective held, outcomes captured in the Roadmap doc.

## 7. Success Metrics (Pilot)

Assessor quality - Inter-rater agreement (competency-level): ≥70% - False-positive rate (Assessor marks “expert”, reviewer disagrees): ≤15% - False-negative rate: ≤15%

Functional completeness - ≥10 pilot interviews without critical bugs - ≥90% coverage of target topics from InterviewPlan - Session duration: 60–90 min

Recruiter / Reviewer UX - Recruiter plan create + approve: ≤15 min - Reviewer annotation: ≤30 min per session - Qualitative NPS: ≥3/5

Reliability - Session completion rate: ≥95% - TurnTrace capture: 100% - LLM latency per turn: ≤15 s

Seed data - ≥50 annotated turns - ≥10 AssessmentCorrections - Avg cost per interview: ≤$1.5

## 8. Risks & Mitigation

| ID | Risk | L | I | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Assessor hallucination (wrong score) | H | H | Variant A correctness prompt + strict JSON schema + mandatory reviewer approval in MVP |
| R2 | Candidate cheating (GPT / Copilot assist) | H | M | Explicit warning prompt, scenario / comparison question types. Phase 2 — serious anti-cheating |
| R3 | Scope creep on a 2-person team | H | H | Freeze scope in W1; new features → Roadmap. Weekly scope review |
| R4 | Weak prompt calibration | M | M-H | Calibration runs in W10, golden dataset in W9, model A/B |
| R5 | Privacy / consent gaps | L | H | Explicit consent flow, Vertex enterprise contract, retention policy in W11 |
| R6 | Vertex cost overrun | L-M | M | Per-session budget, Flash by default, Pro only on final assessment, alert on overrun |
| R7 | Voice-lock-in (architectural, shows up in Phase 3) | L | H (future) | Seven voice-ready guardrails enforced from W1 |

## 9. Dependencies & Resources

People. 2 engineers (Engineer A — backend / ML; Engineer B — frontend / glue). Ihor — tech lead + owner.

Access / infra. - Vertex AI project + billing (approved) - Google Workspace SSO configuration - Git repository (GitHub or GitLab) - Cloud SQL instance (dev + staging + prod) - Staging + production environments

Content. - Competency Matrix (Excel) — C# + React, ready. - ~20 past interview transcripts for seed questions and few-shot examples. - 10 real pilot candidates (pre-agreed with recruiter team).

Internal stakeholders. - Recruiter team — supply candidates, UX feedback. - Security / Privacy — consent flow review. - Tech experts (2–3) — calibration and reviewer annotation.

## 10. Component Inventory (MVP)

| Component | Responsibility | First delivery |
| --- | --- | --- |
| Monorepo + CI | Dev infra | W1 |
| Backend API (FastAPI) | REST + WebSocket endpoints | W1–W2 |
| DB schema (Postgres) | Persistent state | W1–W2 base, then per-feature |
| Matrix importer | Excel → YAML → DB | W2 |
| SSO / Auth | Identity | W1 |
| Position Template | CRUD | W3 |
| Rubric snapshot | Immutable copy on session | W3 |
| State machine (Orchestrator) | Phase control | W4 |
| Interviewer Agent | Generate questions | W4–W5 |
| Assessor Agent | Score answers | W4–W5 |
| TurnTrace logger | Observability storage | W4 |
| Prompts Repository (Git) | Prompt versioning | W4 |
| Cost tracker | LLM spend monitoring | W4 |
| PreInterviewPlanner Agent | Generate plans | W6 |
| InterviewPlan storage | Plan model + freeze | W6 |
| Recruiter Admin UI | Position + plan management | W3, W6 |
| Candidate Session UI | Chat interface | W7 |
| WebSocket engine | Streaming turns | W7 |
| Consent flow | GDPR baseline | W7 |
| Reviewer UI | Post-interview review | W8 |
| TurnAnnotation | Review labels | W8 |
| AssessmentCorrection | Override scoring | W8 |
| Report generation | Recruiter-facing output | W8 |
| Observability dashboards | Ops view | W9 |
| Golden dataset framework | Evals | W9 |
| Alert rules | Cost / latency / errors | W9 |
| Calibration playbook | Process doc | W10 |
| Pilot ops playbook | Runtime doc | W11 |

## 11. Post-MVP Phases (preview)

Detailed scope per phase lives in the Roadmap / Deferred Features document.

Phase 2 — Enhanced Intelligence (~8 weeks post-pilot) - RAG feature-on for Assessor (requires 20–30 annotated sessions) - JD Parser agent (draft Position Template from job description text) - Past-answer statistics in Pre-Interview Review UI - Extended InterviewPlan with skip rules, priority, common pitfalls - Additional tech stacks beyond C# + React - Candidate feedback report

Phase 3 — Voice Trial (~6 weeks) - Gemini Live API integration via Vertex - Voice mode as opt-in - Transcription quality checks - Latency-tuned Assessor path

Phase 4 — Voice Production + Admin UI (~8 weeks) - Voice becomes default - Admin UI for rubric editing (supersedes Configs-as-Code for non-technical users) - Bias / fairness audit capability - Advanced anti-cheating (optional proctoring)

Phase 5 — Fine-tuning (conditional, ~6 weeks) - Only if prompt + RAG hit a ceiling - Requires 500–1000 annotated examples - Assessor fine-tune first

## 12. Glossary

- Rubric / Competency Matrix — tree of Stack → CompetencyBlock → Competency → Topic → Level. Source of truth for scoring.

- Position Template — position spec: stacks, level, must-have competencies, optional. Input to PreInterviewPlanner.

- InterviewPlan — generated session plan (competencies, topics, seed questions, time budget). Frozen snapshot after approval.

- InterviewSession — a single conducted interview.

- TurnTrace — record of one turn: full prompt, raw response, parsed output, tokens, latency, model, agent type. For debug / observability.

- TurnAnnotation — reviewer annotation on one turn (question / answer / assessment quality).

- AssessmentCorrection — reviewer override of Assessor score with reason tags.

- Entry / Specialist / Expert / Proficient — four proficiency levels per topic. Map to Junior / Middle / Senior / Tech Leader.

- Configs-as-Code — rubric, positions, and prompts versioned as YAML in Git.